## Final Gantt Chart
CarSight AI - Final Gantt Chart
Project |  | CarSight AI
Project Manager |  | Lakshya Rastogi
Final Timeline |  | Feb 5 - Apr 20, 2026
Critical Path |  | 75 days
Status |  | Final submission version
[11 empty] | Feb 5 | [6 empty] | Feb 12 | [6 empty] | Feb 19 | [6 empty] | Feb 26 | [6 empty] | Mar 5 | [6 empty] | Mar 12 | [6 empty] | Mar 19 | [6 empty] | Mar 26 | [6 empty] | Apr 2 | [6 empty] | Apr 9 | [6 empty] | Apr 16
WBS | ID | Task | Owner | Start | End | Days | Pred. | Critical | Status | Notes | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1.0 | 1 | Requirements and project scope | Lakshya Rastogi | 2026-02-05 | 2026-02-09 | 5 | - | Yes | 100% | Defined project direction and main deliverables. | bar: Feb 5 5 to Feb 5 9
1.1 | 2 | Literature review and source notes | Lakshya Rastogi | 2026-02-10 | 2026-02-17 | 8 | 1 | No | 100% | Reviewed pricing/NLP background for the report. | bar: Feb 5 10 to Feb 12 17
2.0 | 3 | Used car data collection | Lakshya Rastogi | 2026-02-10 | 2026-02-15 | 6 | 1 | Yes | 100% | Collected listing fields and damage descriptions. | bar: Feb 5 10 to Feb 12 15
2.1 | 4 | Data cleaning and field standardization | Lakshya Rastogi | 2026-02-16 | 2026-02-20 | 5 | 3 | Yes | 100% | Removed missing rows and standardized key fields. | bar: Feb 12 16 to Feb 19 20
3.0 | 5 | NLP text preprocessing | Lakshya Rastogi | 2026-02-21 | 2026-02-25 | 5 | 4 | Yes | 100% | Cleaned damage text and prepared TF-IDF features. | bar: Feb 19 21 to Feb 19 25
3.1 | 6 | Damage type and severity logic | Lakshya Rastogi | 2026-02-26 | 2026-03-02 | 5 | 5 | Yes | 100% | Mapped text to body, engine, interior, and severity signals. | bar: Feb 26 26 to Feb 26 2
3.2 | 7 | Structured + text feature engineering | Lakshya Rastogi | 2026-03-03 | 2026-03-06 | 4 | 6 | Yes | 100% | Combined car attributes with text-derived features. | bar: Feb 26 3 to Mar 5 6
4.0 | 8 | Regression pricing model | Lakshya Rastogi | 2026-03-07 | 2026-03-11 | 5 | 7 | Yes | 100% | Trained baseline price prediction model. | bar: Mar 5 7 to Mar 5 11
4.1 | 9 | Model evaluation and price range logic | Lakshya Rastogi | 2026-03-12 | 2026-03-14 | 3 | 8 | Yes | 100% | Checked MAE/RMSE and converted output to a range. | bar: Mar 12 12 to Mar 12 14
5.0 | 10 | Backend API pipeline | Lakshya Rastogi | 2026-03-15 | 2026-03-20 | 6 | 9 | Yes | 100% | Built API flow from input to model response. | bar: Mar 12 15 to Mar 19 20
5.1 | 11 | Frontend dashboard prototype | Lakshya Rastogi | 2026-02-21 | 2026-02-28 | 8 | 4 | No | 100% | Created input form, result panel, and explanation area. | bar: Feb 19 21 to Feb 26 28
5.2 | 12 | End-to-end integration | Lakshya Rastogi | 2026-03-21 | 2026-03-24 | 4 | 10, 11 | Yes | 100% | Connected frontend, backend, NLP, and model output. | bar: Mar 19 21 to Mar 19 24
5.3 | 13 | Chatbot explanation layer | Lakshya Rastogi | 2026-03-25 | 2026-03-28 | 4 | 12 | Yes | 100% | Added simple assistant responses for valuation questions. | bar: Mar 19 25 to Mar 26 28
6.0 | 14 | System testing and fixes | Lakshya Rastogi | 2026-03-29 | 2026-04-02 | 5 | 13 | Yes | 100% | Tested NLP output, API response, UI flow, and edge cases. | bar: Mar 26 29 to Apr 2 2
7.0 | 15 | Final report and Turnitin proof | Lakshya Rastogi | 2026-04-03 | 2026-04-10 | 8 | 2, 14 | Yes | 100% | Prepared final written deliverable and similarity proof page. | bar: Apr 2 3 to Apr 9 10
7.1 | 16 | Final PPT and recording prep | Lakshya Rastogi | 2026-04-11 | 2026-04-15 | 5 | 15 | Yes | 100% | Built final deck and practiced recording flow. | bar: Apr 9 11 to Apr 9 15
7.2 | 17 | GitHub cleanup and submission package | Lakshya Rastogi | 2026-04-16 | 2026-04-20 | 5 | 16 | Yes | 100% | Final code cleanup, README, and upload package. | bar: Apr 16 16 to Apr 16 20

## Critical Path
CarSight AI - Critical Path Analysis
Critical Path | 1 -> 3 -> 4 -> 5 -> 6 -> 7 -> 8 -> 9 -> 10 -> 12 -> 13 -> 14 -> 15 -> 16 -> 17
Total Duration | 75 days
Interpretation | Any delay on a zero-slack task would delay the final submission package.
ID | Activity | Duration | Pred. | ES | EF | LS | LF | Slack | Critical? | Notes
1 | Requirements and project scope | 5 | - | 0 | 5 | 0 | 5 | 0 | Yes | On critical path
2 | Literature review and source notes | 8 | 1 | 5 | 13 | 49 | 57 | 44 | No | Has scheduling slack
3 | Used car data collection | 6 | 1 | 5 | 11 | 5 | 11 | 0 | Yes | On critical path
4 | Data cleaning and field standardization | 5 | 3 | 11 | 16 | 11 | 16 | 0 | Yes | On critical path
5 | NLP text preprocessing | 5 | 4 | 16 | 21 | 16 | 21 | 0 | Yes | On critical path
6 | Damage type and severity logic | 5 | 5 | 21 | 26 | 21 | 26 | 0 | Yes | On critical path
7 | Structured + text feature engineering | 4 | 6 | 26 | 30 | 26 | 30 | 0 | Yes | On critical path
8 | Regression pricing model | 5 | 7 | 30 | 35 | 30 | 35 | 0 | Yes | On critical path
9 | Model evaluation and price range logic | 3 | 8 | 35 | 38 | 35 | 38 | 0 | Yes | On critical path
10 | Backend API pipeline | 6 | 9 | 38 | 44 | 38 | 44 | 0 | Yes | On critical path
11 | Frontend dashboard prototype | 8 | 4 | 16 | 24 | 36 | 44 | 20 | No | Has scheduling slack
12 | End-to-end integration | 4 | 10, 11 | 44 | 48 | 44 | 48 | 0 | Yes | On critical path
13 | Chatbot explanation layer | 4 | 12 | 48 | 52 | 48 | 52 | 0 | Yes | On critical path
14 | System testing and fixes | 5 | 13 | 52 | 57 | 52 | 57 | 0 | Yes | On critical path
15 | Final report and Turnitin proof | 8 | 2, 14 | 57 | 65 | 57 | 65 | 0 | Yes | On critical path
16 | Final PPT and recording prep | 5 | 15 | 65 | 70 | 65 | 70 | 0 | Yes | On critical path
17 | GitHub cleanup and submission package | 5 | 16 | 70 | 75 | 70 | 75 | 0 | Yes | On critical path

## Notes
Planning Notes
Purpose | Final schedule artifacts for the CarSight AI DS 440 capstone project.
Date Basis | Dates are shown as calendar project days from February 5 to April 20, 2026.
Critical Path Meaning | The critical path is the longest dependent task chain from planning to final submission.
Color Key | Red = critical path task; blue = non-critical task; light gray = weekend/background cells.
Status | All tasks are marked complete for the final submission version.
Report Use | The Critical Path PNG can be inserted directly into the final report or presentation.
Student Note | The chart is intentionally simple and readable rather than over-designed.